## Read me
HIT339 Group 16: traceability and billable hours
Version 1.1, 16 October 2026. Release documented: main at b695674 (application code as at 55fbc1d). Synchronised with the group portfolio.
Requirements RTM: every brief requirement with its owner, code, tests, evidence and gap.
User stories: the 16 user stories with their screens, flows and tests.
Billable tasks: tasks, allocations, 12 October planning estimates and the actual hours each member entered. Ashesh's actual hours are retrospective estimates made on 16 October 2026 from the commits and pull requests, not recorded timesheets. Estimates are not hours worked.
Totals: formulas over the Billable tasks sheet.
Time log: one row per recorded work session (Susan and Milan). Ashesh kept no time log; his hours are per-task estimates in Billable tasks.
Yellow cells are hours still to be entered by the member concerned.

## Requirements RTM
ID | Source | Requirement | Owner | Implementation | Tests (methods) | Evidence | Status | Gap / to confirm
PA-1 | Brief Part A | Installation and running instructions from Git for each branch location; tested on the VM | Ashesh | Installation Manual; README | 374 tests passed on macOS and on Milan's and Susan's Windows 11 PCs (16 Oct) | Installation Manual step 9: Windows PC test record and screenshots | Met on Windows PCs; designated VM test pending | Designated VM test being arranged by Susan; results pending
PA-2 | Brief Part A | User guide (manual and/or video) for patrons to use search | Susan | Patron User Guide | Screens verified against the running app | Screenshots P01-P16 | Met (manual)
PA-3.1 | Brief Project Plan 1 | Team contracts | All | Team Contract |  |  | Met | Ashesh to sign (Susan and Milan signed on 08/10/2026)
PA-3.2 | Brief Project Plan 2 | Requirements document and notes | Ashesh | Requirements Document; this workbook |  | Section docs in repo | Met
PA-3.3 | Brief Project Plan 3 | Team's approach | Ashesh | Development Approach |  | Git history | Met
PA-3.4 | Brief Project Plan 4 | Links to PM sites with read credentials for the lecturer; trial lasts 2 weeks past submission | Ashesh | PM and Repository Access |  | Public GitHub repository | Met | Repository public since 16 Oct 2026; no invitation needed
PA-3.5 | Brief Project Plan 5 | Billable tasks with hours and allocations | Ashesh | Billable Tasks; sheet "Billable tasks" |  | 12 Oct estimates | Met | Ashesh's actual hours are retrospective estimates; some of Susan's and Milan's portfolio tasks have no hours entered
PA-3.6 | Brief Project Plan 6 | Meeting minutes | All | Meeting minutes M-01 and M-02 (portfolio 10.3); coordination records PCR-01 to PCR-15 |  | GitHub PRs; Git history; SECTION3_NOTES.md | Met
PA-3.7 | Brief Project Plan 7 | Team's strengths and weaknesses | All | Strengths, Weaknesses and Reflection |  | Git and PR evidence | Met
D-1 | Brief deliverables | Portfolio PDF with PM artefacts, integration diagrams, user journey maps | All | Group Portfolio |  | Diagrams D01-D05, F01-F06; journeys J01-J04; storyboards, sketches, wireframes | Met
D-2 | Brief deliverables | Repository with .NET 10 solution; README on modules, multi-branch seeding, testing | Ashesh | README.md on main; net10.0 | All tests: 374 at 55fbc1d and at b695674 | main b695674 | Met
R1 | Brief Part B 1 | Public self-service kiosk: touch-friendly; scan a code to check out or view account summary | Susan (+ Ashesh integration) | KioskController, KioskService, KioskSessionStore, KioskPinService, Views/Kiosk | KioskControllerTests 26, KioskServiceTests 14, KioskSessionTests 16, KioskPinTests 39 | P08-P16; V08-V10 | Met
R2 | Brief Part B 1 | Secure read-only REST API: items, categories, operating status | Susan | CatalogueApiController, Api/ | CatalogueApiTests 16 | I15; docs/SECTION2_API.md | Met
R3 | Brief Part B 2 | Simulated email/SMS notifications when borrowed, nearing due date, accruing fines | Milan; overdue fine notices by Ashesh | NotificationService, DueDateReminderService (incl. SendOverdueFineNoticesAsync), NotificationsController | NotificationAndQueueTests 8, DueDateReminderServiceTests 5, OverdueFineNoticeTests 21 | I12; Milan screenshots 01, 02, 09, 13; screenshot 18 (FineAccruing) | Met | Overdue notices at most once per loan every 7 days; reminders and notices triggered by the staff due-date check; commit ba03b3c
R4 | Brief Part B 2 | Multi-branch inventory: items and desks track branch; inter-branch transfers | Ashesh | Branch, ItemTransfer, BranchesController, TransfersController, TransferService | BranchIntegrationTests 26, BranchesControllerTests 17, TransferTests 35 | I02-I06, I11 | Met
R5 | Brief Part B 2 | Reservation and waitlist on Borrowed or Damaged items; notify next person when Available | Milan (+ Ashesh integration) | Reservation, ReservationService, ReservationsController | NotificationAndQueueTests, ReservationExpiryTests 4, IntegrationFixTests 46 | I13; Milan screenshots 03-12 | Met
R6 | Brief Part B 3 | Bulk import via CSV or mock metadata provider | Susan | ImportController, ItemImportService, CsvReader | ItemImportServiceTests 16 | I14; docs/samples | Met (CSV) | No mock provider (optional)
R7 | Brief Part B 3 | Manager analytics export CSV/PDF: borrowing statistics, fine revenue audit, inventory health | Ashesh | ManagerController, ReportService, ReportCsvWriter, ReportPdfService | ReportTests 44 | I10 | Met
NF-1 | Brief deliverables | .NET 10 | Ashesh | net10.0; EF Core 10.0.13; global.json | Full suite on .NET 10: macOS and two Windows 11 PCs | Commit a353210 | Met | Designated VM test pending
NF-2 | Brief Part A | Runs on the lab VM (Windows) | All | Installation Manual; docs/WINDOWS_VM_CHECKLIST.md | Windows 11 PC tests (Milan, Susan): 374 passed; nine installation checks passed | Installation Manual step 9 | Partly met: designated VM test pending | Susan is arranging the designated VM test
NF-3 | Group | Assignment 2 data survives upgrade | Ashesh | 7 migrations | Migration tests on a copy of the database |  | Met
NF-6 | Group | Security: roles, anti-forgery, API key, rate limits, hashed PIN, no secrets in docs | All | Program.cs, ApiKeyFilter, KioskPinService | KioskPinTests, CatalogueApiTests, IntegrationFixTests |  | Met | Known limits in README

## User stories
ID | Persona | Story (I want to...) | Priority (MoSCoW) | Screens | Flow / diagram | Tests | Status
US-01 | Patron (Priya) | Search the catalogue by title word or code with filters | Must | Public Search | F01 | HomeControllerTests, BranchIntegrationTests | Met
US-02 | Patron (Priya, Alice) | Kiosk sign-in with card and PIN | Must | Kiosk welcome | F02, F06 | KioskPinTests, KioskSessionTests, KioskControllerTests | Met
US-03 | Patron | Borrow at the kiosk by scanning the code | Must | Kiosk account | F02 | KioskServiceTests, IntegrationFixTests | Met
US-04 | Patron (Alice) | See loans, due dates, fines and holds | Must | Kiosk account | F02 | KioskControllerTests, KioskSessionTests | Met
US-05 | Patron (Alice) | Reserve an item that is out | Must | Reservations | F03 | NotificationAndQueueTests, ReservationExpiryTests, IntegrationFixTests | Met
US-06 | Patron (Alice) | Be told when borrowing, nearly due, fined | Must | Notifications | F04 | NotificationAndQueueTests, DueDateReminderServiceTests, OverdueFineNoticeTests | Met
US-07 | Reception (Grace) | Lend and return only my branch's items | Must | Loans | D04 | BranchIntegrationTests, LoansControllerTests | Met
US-08 | Reception (Grace) | Request and track transfers | Must | Transfers | F05 | TransferTests | Met
US-09 | Reception (Grace) | Set or reset a kiosk PIN | Must | Borrowers, Set PIN | F02 | KioskPinTests | Met
US-10 | Admin (Ahmed) | Set up a branch and its Reception account | Must | Branches, Staff | D04, Storyboard 3 | BranchesControllerTests, StaffControllerTests | Met
US-11 | Admin (Ahmed) | Import many items from CSV | Must | Import | Susan journey 3 | ItemImportServiceTests | Met
US-12 | Manager (Daniel) | Export reports as CSV and PDF | Must | Statistics | J04 | ReportTests | Met
US-13 | Developer (Sam) | Query catalogue through a read-only API | Must | API JSON | Susan journey 2 | CatalogueApiTests | Met
US-14 | Library IT staff | Install at a new location with one manual | Must | Installation Manual | D04 | Manual test on macOS | Partly met (VM outstanding)
US-15 | Reception (Grace) | Expire uncollected holds | Should | Reservations | F03 | ReservationExpiryTests | Met
US-16 | Patron (Alice) | Set or change my own PIN | Could | Not built |  |  | Not built

## Billable tasks
ID | Area | Task | Allocated to | Estimated hours (12 Oct) | Actual hours | Deliverable | Status
G-01 | Shared | Analyse the brief and agree the split into three sections | All | 9 |  | Agreed scope and section owners | Done before 11 Oct
G-02 | Shared | Team coordination and meetings | All | 12 |  | Coordination records | Done; see coordination records
G-03 | Shared | Integration testing of all sections | All | 9 |  | Test records | Done: macOS (Ashesh), Windows 11 PCs (Milan, Susan); designated VM test pending
G-04 | Shared | Final submission preparation and portfolio review | All | 6 |  | Submitted portfolio and repository | Ready for final review
S1-01 | Section 1 | Review baseline; design branch and transfer model | Ashesh | 3 | 2 | docs/SECTION1_MULTIBRANCH_ANALYTICS.md | Done, merged (PR #1)
S1-02 | Section 1 | Database design and migrations; upgrade test on a copy of the Assignment 2 database | Ashesh | 4 | 3 | AddBranchesAndTransfers, AddItemMovementKind | Done, merged (PR #1)
S1-03 | Section 1 | Branch management backend and views | Ashesh | 4 | 2.5 | BranchesController, Views/Branches | Done, merged (PR #1)
S1-04 | Section 1 | Branches in items, staff, loans, public search, seeder, navigation | Ashesh | 5 | 3 | Updated controllers and views | Done, merged (PR #1)
S1-05 | Section 1 | Inter-branch transfer workflow | Ashesh | 7 | 4.5 | TransferService, TransfersController | Done, merged (PR #1)
S1-06 | Section 1 | Location correction and cross-branch returns with movement history | Ashesh | 3 | 2 | CorrectBranch action, item movements | Done, merged (PR #1)
S1-07 | Section 1 | Report service: borrowing, fine revenue audit, inventory health | Ashesh | 6 | 3.5 | ReportService | Done, merged (PR #1)
S1-08 | Section 1 | CSV export with safe escaping | Ashesh | 2 | 1 | ReportCsvWriter | Done, merged (PR #1)
S1-09 | Section 1 | PDF export | Ashesh | 3 | 2 | ReportPdfService | Done, merged (PR #1)
S1-10 | Section 1 | Manager dashboard and report pages; responsive styling | Ashesh | 4 | 2 | Views/Manager, site.css | Done, merged (PR #1)
S1-11 | Section 1 | Automated tests for Section 1 and baseline regressions | Ashesh | 8 | 4 | 132 test cases | Done, merged (PR #1)
S1-12 | Section 1 | Quality assurance and defect fixes | Ashesh | 4 | 1.5 | QA results in Section 1 document | Done, merged (PR #1)
S1-13 | Section 1 | Diagnose and fix the Windows-only SQLite test failure | Ashesh | 1.5 | 1 | b1f9453 | Done, merged (PR #2)
S1-14 | Section 1 | Section 1 technical documentation | Ashesh | 3 | 1.5 | docs/SECTION1_MULTIBRANCH_ANALYTICS.md | Done, merged (PR #1)
S2-01 | Section 2 | Requirements analysis and design: kiosk, API, import | Susan | 3 | 1 | docs/SECTION2_REQUIREMENTS.md | Done, merged (PR #4)
S2-02 | Section 2 | Kiosk front end: branch selection, welcome, account screens | Susan | 6 | Done with Claude (see 2.11) | Views/Kiosk, kiosk.css | Done, merged (PR #4)
S2-03 | Section 2 | Kiosk back end: patron identification and checkout | Susan | 7 | Done with Claude (see 2.11) | KioskController, KioskService | Done, merged (PR #4)
S2-04 | Section 2 | Read-only REST API endpoints | Susan | 6 | Done with Claude (see 2.11) | CatalogueApiController | Done, merged (PR #4)
S2-05 | Section 2 | API response models, filtering, API key, rate limit, documentation | Susan | 3 | Done with Claude (see 2.11) | Api/, docs/SECTION2_API.md | Done, merged (PR #4)
S2-06 | Section 2 | CSV import back end: parsing and validation | Susan | 6 | Done with Claude (see 2.11) | ItemImportService, CsvReader | Done, merged (PR #4)
S2-07 | Section 2 | CSV import front end: upload page and report | Susan | 4 | Done with Claude (see 2.11) | ImportController, Views/Import | Done, merged (PR #4)
S2-08 | Section 2 | Database changes and migrations, if required | Susan | 2 | 0 (not needed) | None needed | Not needed: Section 2 added no migration
S2-09 | Section 2 | Automated tests for Section 2 | Susan | 8 | 0.25 | 4 test files (69 test methods) | Done, merged (PR #4)
S2-10 | Section 2 | Debugging and integration with branches and reservations | Susan | 4 | 0.75 | Branch built on Section 3 | Done, merged (PR #4)
S2-11 | Section 2 | Section 2 documentation: notes, user guide, API reference, journeys | Susan | 3 | 0.5 | docs/SECTION2_*.md | Done, merged (PR #4)
S3-01 | Section 3 | Requirements analysis and design: reservations, waitlist, notifications | Milan | 3 | 2 | docs/SECTION3_NOTES.md | Done, merged (PR #3)
S3-02 | Section 3 | Notification model and migration | Milan | 2 | 1.5 | Notification, AddNotifications | Done, merged (PR #3)
S3-03 | Section 3 | Notification service | Milan | 3 | 2.5 | NotificationService | Done, merged (PR #3)
S3-04 | Section 3 | Notifications on borrow and on fine | Milan | 3 | 2.5 | LoansController changes | Done, merged (PR #3)
S3-05 | Section 3 | Notifications dashboard and menu link | Milan | 4 | 3 | NotificationsController, Views/Notifications | Done, merged (PR #3)
S3-06 | Section 3 | Reservation model and migration | Milan | 2 | 2 | Reservation, AddReservations | Done, merged (PR #3)
S3-07 | Section 3 | Reservation placement and cancellation | Milan | 6 | 3.5 | ReservationsController | Done, merged (PR #3)
S3-08 | Section 3 | Waitlist: notify the next borrower when an item is available | Milan | 5 | 3 | ReservationService | Done, merged (PR #3)
S3-09 | Section 3 | Due-soon reminders and hold expiry | Milan | 5 | 3.5 | DueDateReminderService, expiry | Done, merged (PR #3)
S3-10 | Section 3 | Reservation views; integration with branches | Milan | 4 | 2 | Views/Reservations | Done, merged (PR #3)
S3-11 | Section 3 | Automated tests for Section 3 | Milan | 8 | 3 | 3 test files (17 test methods) | Done, merged (PR #3)
S3-12 | Section 3 | Debugging, merging latest main, pull request | Milan | 4 | 2 | PR #3 | Done, merged (PR #3)
S3-13 | Section 3 | Section 3 documentation and screenshots | Milan | 3 | 2 | docs/SECTION3_NOTES.md, 17 screenshots | Done, merged (PR #3)
X-01 | Cross-cutting | Upgrade to .NET 10 and retest | Ashesh | 4 | 0.5 | a353210 | Done, merged (PR #5)
X-02 | Cross-cutting | Add .gitignore; stop tracking bin/, obj/ and library.db | Ashesh | 1 | 0.5 | PR #7 (7c28183) | Done, merged (PR #7)
X-03 | Cross-cutting | Test the Windows fix (PR #2) on Windows 11 | Teammate on Windows 11 | 1 | 0.5 | Test result | Done 12 Oct, before PR #2 was merged
INT-01 | Integration | Review all sections together; 10 cross-section fixes with 34 regression tests | Ashesh | not estimated | 9 | fbd1dd3 to 8c1fd29 | Done, merged (PR #5)
INT-02 | Integration | Windows test of the integration branch | Milan | not estimated | 0.5 | Test feedback | Done 15 Oct; reported to Ashesh
INT-03 | Integration | Kiosk: signed-out screen with link to main site (from Milan's test) | Ashesh | not estimated | 1 | dffb826 | Done, merged (PR #5)
INT-04 | Integration | Kiosk: server-side sessions so sign-out cannot be undone | Ashesh | not estimated | 4 | 4972da4 | Done, merged (PR #5)
INT-05 | Integration | Kiosk: 6-digit PIN set by staff, with lockout | Ashesh | not estimated | 5 | 6584094 | Done, merged (PR #5)
INT-06 | Integration | Kiosk navigation, sign-in design and accessible validation | Ashesh | not estimated | 3 | 6969578, af8e002 | Done, merged (PR #5)
INT-07 | Integration | Merge PRs #3 to #5 and verify a fresh clone of main | Ashesh | not estimated | 2 | 4b8862f; 353 tests pass | Done
INT-08 | Integration | Overdue fine notices for R3, extending the Section 3 due-date check | Ashesh | not estimated | 3 | ba03b3c; merge 55fbc1d; 374 tests pass | Done, merged (PR #6)
PM-01 | Project management | Project plan and development approach | Ashesh | 3 | 1.5 | Development Approach | Done
PM-02 | Project management | Task allocation and estimated hours | Ashesh | 1.5 | 1 | Billable Tasks | Done
PM-03 | Project management | Repository management | Ashesh | 3 | 1.5 | Project management sites and repository | Done
PM-04 | Project management | Installation and running instructions | Ashesh | 2 | 2 | Installation Manual | Done
PM-05 | Project management | README | Ashesh | 1.5 | 1 | README.md | Done, merged (PR #5)
PF-01 | Portfolio | Patron user guide | Susan | 6 |  | Patron User Guide | Done
PF-02 | Portfolio | Requirements document and notes | Susan | 4 |  | Requirements | Done
PF-03 | Portfolio | Deployment and test on the designated VM | Susan | 3 | 1 | VM test record | Windows 11 PC tests done (Milan, Susan; see step 9); designated VM test pending, being arranged by Susan
PF-04 | Portfolio | Team contract | Susan | 2 |  | Team Contract | Done; signed by Susan and Milan, Ashesh's signature to be added
PF-05 | Portfolio | Meeting minutes and coordination records | Milan | 4 |  | Coordination records | Done
PF-06 | Portfolio | Team strengths and weaknesses | Milan | 2 |  | Strengths and weaknesses | Done
PF-07 | Portfolio | Project-management site details and lecturer read access | Ashesh | 2 | 1 | Project management sites | Done; repository made public on 16 Oct, so no invitation is needed
PF-08 | Portfolio | Integration diagrams and user journey maps | Ashesh | 4 | 2 | System design; UX design | Done
PF-09 | Portfolio | UX design: personas, storyboards, sketches, wireframes, journeys | Ashesh | not estimated | 3 | UX Research and Design | Done
PF-10 | Portfolio | Assemble the portfolio, hand-over and PDF | Ashesh | not estimated | 5.5 | Group Portfolio | Done

## Totals
Member | Estimated hours (own tasks) | Share of "All" tasks | Estimated total | Actual hours (own tasks)
Ashesh
Susan
Milan
Unassigned |  | 0
Total
Estimates are planning figures from 12 October 2026, not hours worked. Expected estimated total: 241.5 hours.
Susan's total of 3.75 hours in the portfolio also includes 0.25 hours on the shared task G-04 (see Time log). Ashesh's 80 hours are retrospective estimates.

## Time log
Date | Member | Task ID | What was done | Hours
11/10/2026 | Milan Sapkota | S3-02, S3-03, S3-04 | Notification model, service, borrow and fine notifications (including setup and first run) | 2.5
12/10/2026 | Milan Sapkota | S3-05 | Notifications dashboard and menu link | 1
12/10/2026 | Milan Sapkota | S3-06, S3-07 | Reservation model, migration, placing and cancelling | 2
12/10/2026 | Milan Sapkota | S3-08 | Notify the next borrower on return; updated loan tests | 1.5
13/10/2026 | Milan Sapkota | S3-12, S3-10 | Merged main; reservation views and service | 1.5
13/10/2026 | Milan Sapkota | S3-13 | Testing and reservation screenshots | 1
13/10/2026 | Milan Sapkota | S3-08 | Notify queue on Admin change; Ready items kept for first borrower | 1.5
13/10/2026 | Milan Sapkota | S3-09, S3-11 | Due-date reminders, hold expiry and tests | 2.5
13/10/2026 | Milan Sapkota | S3-13, S3-12 | README section; opened PR #3 | 0.5
15/10/2026 | Milan Sapkota | INT-02 | Windows test of the integration branch and feedback | 1.5
16/10/2026 | Milan Sapkota | INT-02 | Windows retest of final main and installation checks | 1.5
13/10/2026 | Susan Acharya | S2-01 | Read the brief and the Section 2 scope, cloned the repository and drafted Section 2 with Claude (estimate) | 1
13/10/2026 | Susan Acharya | S2-10, S2-09 | Moved my branch onto Section 3, added the Section 2 files, built and ran the app, tried the kiosk and ran all 238 tests | 0.75
13/10/2026 | Susan Acharya | S2-10 | Committed and pushed Section 2, opened PR #4 against the Section 3 branch and told the team | 0.25
13/10/2026 | Susan Acharya | S2-11 | Section 2 pages for the portfolio | 0.5
16/10/2026 | Susan Acharya | G-04 | Read the portfolio and signed the team contract | 0.25
16/10/2026 | Susan Acharya | PF-03 | Windows test of the final main (374 passed) and the nine installation checks in Edge and Firefox, with screenshots | 1